## TODO LIST --> general view
TODO for Re-Fashionable
# | Activity | Responsible | Deadline | Output description | Link to output (if applicable) | Status
WP1: Project Management (BRI)
T1.1 | Set up project management structure and processes | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports and ensure that improvements have been made when needed. | TODO for Re-Fashionable | done
T1.2 | Project coordination and monitoring | BRI | 2025-08-31 | BRI will set up project management structure and processes and is also responsible for Project coordination and monitoring. It will write the Interim and Final project reports and make sure that all partners have contributed with their responsibilities as assigned by the proposal. | T1.1 REFA PM Handbook.docx | ongoing
T1.3 | Set up quality assurance plan | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports, and ensure that improvements have been made when needed. | T1.3 REFA Quality Assurance Plan.docx | done
T1.4 | Quality assurance activities and reports | BRI | 2025-08-31 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports, and ensure that improvements have been made when needed. |  | ongoing
T1.5 | Kick off meeting in Girona | BRI | 2023-12-12 | A kick-off meeting will be hosted in Lucca by the Machiavelli --> in Girona by BRI, changed | [Re-Fashionable] - AdminProject | done
T1.6 | 2nd meeting Budapest | EKO | 2024-04-24 | EKO will organize the 2nd project meeting and the “Pop up event”, both in Budapest. |  | ongoing
T1.7 | 3rd meeting Lucca | Machiavelli | 2024-12-15 | Machiavelli will organize the the 3rd project meeting and the “Pop up event in Lucca”. |  | not started
T1.8 | Interim report | BRI | 2024-09-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners, evaluating: -Collaboration and coordination -Risks and how they are mitigated -Understanding of roles, tasks and deliverables per partner -Partners’ expectations of the usage of project results |  | not started
T1.9 | Final report | BRI | 2025-08-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners |  | not started
WP2: “Re-Fashionable” digital platform (BRI)
T2.1 | Mapping of stakeholders | QSTURA | 2024-02-01 | A database of stakeholders extended to all partner countries (SP, IT,EL, HU, NL) with Fashion professionals, Fashion Companies,Students, Environmental Organization - with 10 members per category (50 members per partner, or 300 members in total). | Mapping of Stakeholders | done
T2.2 | Development of the specifications of the "Re-fashionable" digital platform | ALL PARTNERS | 2024-04-15 | IDEC will create and suggest in a report, based on its past experience the specifications (functions, modus-operandi, interface, menu etc.), of the platform. Partners will be able to comment and suggest improvements and/or changes. | T2.3 Platform definition – Re-fashionable | ongoing
T2.3 | Technical development of the platform | BRI | 2024-06-30 | BRI's technical staff will create and deliver the platform in a functional and user-friendly way. |  | ongoing
T2.4 | Translation of the digital platform | ALL PARTNERS | 2024-08-15 | Partners will deliver the texts to be included in the platform in their national languages. |  | not started
T2.5 | On boarding activities for attracting platform subscribers | QSTURA | ask silvia! | Qstura will guide the partners on presenting the platform in Workshops, participation in events, fairs and conferences |  | not started
T2.6 | Promoting the digital platform | BRI | 2024-09-07 | BRI will direct the partners on promoting the platform through publicity in relevant traditional and online media such as magazines, newspapers, portals, radio and blogs. |  | not started
T2.7 | Pilot operation of the platform - matchmaking | BRI | 2024-09-15 | BRI will direct the pilot usage of the platform by registered members, give instructions and support and implement technical changes if necessary. |  | not started
WP3: "Re-Fashionable" e-learning course (IDEC + Machiavelli)
T3.1 | Organisation of focus groups: Definition of target group, objectives and expected results | IDEC | 2024-02-09 | Both through the mapping of stakeholders from the previous WP and their existing networks, partners, guided by Blue Room, will organize structured focus groups to derive measurable results on what to include in the curriculum of the course |  | ongoing
T3.2 | Creation of training curriculum | IDEC | 2024-02-28 | Based on the results of the focus groups from the previous task, Blue Room will create and deliver to partners a complete curriculum about the thematics of sustainable fashion procedures |  | not started
T3.3 | Developement of e-learning course contents | IDEC | 2024-03-15 | All partners under the leadership of IDEC will create contents based on expertise per module and deliver it complete with theoretical, practical content and self-assessment quiz. 24 |  | not started
T3.4 | English | IDEC | 2024-05-31 | IDEC will supervise the final transformation of the created contents into a complete, well-crafted, all-inclusive course in respect to the curriculum and templates provided beforehand. |  | not started
T3.5 | Peer review | EKO | 2024-06-30 | EKO will lead the Peer review, a task whose purpose is to check, evaluate, add any omitted content and perfect the course. This task will be done in an orderly, organized manner and suggestions will be implemented promptly. |  | not started
T3.6 | Translation | IDEC | 2024-08-31 | The translation to all partner languages by the respective partner in SP, IT, EL, HU, NL. The supervisor’s role will be to check that all contents have been translated and the national courses are ready for piloting. |  | not started
T3.7 | Pilot delivery of e-learning course | Machiavelli | 2024-09-01 | Machiavelli will guide the piloting by 15 members of the target groups per country. Each partner will deliver a piloting report. It will provide guidelines on the process, evaluation techniques and manner of implementation of improvements | In WP3, the school is responsible for Pilot delivery of e-learning course, overseeing that all partners contribute and submit their reports. Before and during the Summer Lab it will direct the Development of video - stories by participants and give them guidelines as needed. It will organize the Kick-off meeting in Lucca and the “Pop up event in Lucca”. | not started
WP4: Re-Fashionable Summer Lab (LHF)
T4.1 | Design of summer lab | LHF | 2024-09-30 | L.H.F. will prepare an agenda and design the tasks, find the ideal trainers and create an exact plan on how the project goals and the previous steps of the project will be integrated in the programme to better reach the project’s objectives. |  | not started
T4.2 | Call for participants | LHF | 2024-12-01 | L.H.F. will provide the other partner organizations ,with two different participant’s profiles, one for trainer/staff and one for student, so that each partner will have a clear and goal-oriented tool to select which people to send to the Lab. |  | not started
T4.3 | Selection of participants | LHF | 2025-01-01 | Partners will send a list of eligible profiles to L.H.F. and it will evaluate them and make the final selection according to predefined Key Performance Indicators. Thus, the final list of the 22 participants will be created. |  | not started
T4.4 | Preparation of participants | LHF | 2025-05-01 | L.H.F. will create a document with all the necessary information and things to be prepared and send it to all partners so that they can prepare their participants for the Lab |  | not started
T4.5 | Organisation of Summer lab | ALL PARTNERS | 2025-07-01 | L.H.F. will select the venue and brief the trainers involved and host the participants at its premises. All partners’ responsibility for that task is to make travel arrangements and send the participants. |  | not started
T4.6 | Summer Lab | LHF | 2025-08-01 | Development of video - stories from the Summer Lab: This final task is the responsibility of the Machiavelli Fashion School, which has the technical experience to guide participants in documenting the Summer Lab in 3 video stories. |  | not started
WP5: Dissemination and impact (EKO)
T5.1 | Develop Dissemination and Exploitation plan | EKO | 2023-12-31 | A 360o (from concept to materialization to feedback and application of corrective actions) plan will be created by EKO and delivered at the kickoff meeting. | [link to file on Admin[ | ongoing
T5.2 | Development of the project identity (logos, graphic templates): an attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | EKO | 2023-12-31 | An attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | [link to file on Admin[ | not started
T5.3 | Development of project website | EKO | 2024-01-31 | ΕΚΟ will create an inclusive and user friendly website in EN, EL, SP,IT, HU, NL update it as the project progresses and track visitors. | [link to file on Admin[ | ongoing
T5.4 | Development of leaflet and roll-up | EKO | 2024-01-31 | EKO will also create a leaflet and a rollup and deliver it to partners to translate and adapt so that they can use them for communicating with targets and during events. | [link to file on Admin[ | ongoing
T5.5 | Publication of articles | EKO | 2025-07-01 | ΕΚΟ will oversee that in stage of the project, partners have composed and published interesting articles in their national media, regarding the new evolvements of the project. |  | not started
T5.6 | Social media creation and animation | EKO | 2025-07-01 | ΕΚΟ will create the Facebook and Instagram accounts, and make a schedule of posts for partners to follow so that there is constant and interesting presence and useful content generated. |  | not started
T5.7 | Transnational conference in Friesland | LHF | 2025-07-01 | It will be organised by LUF and will coincide with the culmination of the Summer Lab. The 30 participants of the event that are members of the target groups, will have the opportunity to learn the results of the Lab, presented by its own participants |  | not started
T5.8 | Pop up event in Girona | BRI | 2025-06-01 | Blue Room will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia |  | not started
T5.9 | Pop up event in Piraeus | IDEC | 2025-06-01 | IDEC will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. |  | not started
T5.10 | Pop up event in Lucca | Machiavelli | 2025-06-01 | Machiavelli will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. |  | not started
T5.11 | Pop up event in Szeged | EKO | 2025-06-01 | EKO will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. |  | not started

## TODO LIST --> view with filters
TODO for Re-Fashionable
T1.5 | Kick off meeting in Girona | BRI | 2023-12-12 | A kick-off meeting will be hosted in Lucca by the Machiavelli --> in Girona by BRI, changed | [Re-Fashionable] - AdminProject | done
T5.1 | Develop Dissemination and Exploitation plan | EKO | 2023-12-31 | A 360o (from concept to materialization to feedback and application of corrective actions) plan will be created by EKO and delivered at the kickoff meeting. | [link to file on Admin[ | done
T5.2 | Development of the project identity (logos, graphic templates): an attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | EKO | 2023-12-31 | An attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | [Re-Fashionable] - AdminProject | done
T1.1 | Set up project management structure and processes | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports and ensure that improvements have been made when needed. | TODO for Re-Fashionable | done | T1.1 REFA PM Handbook.docx
T1.3 | Set up quality assurance plan | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports, and ensure that improvements have been made when needed. | T1.3 REFA Quality Assurance Plan.docx | done
T5.3 | Development of project website | EKO | 2024-01-31 | ΕΚΟ will create an inclusive and user friendly website in EN, EL, SP,IT, HU, NL update it as the project progresses and track visitors. | [link to file on Admin[ | ongoing
T5.4 | Development of leaflet and roll-up | EKO | 2024-01-31 | EKO will also create a leaflet and a rollup and deliver it to partners to translate and adapt so that they can use them for communicating with targets and during events. | https://docs.google.com/spreadsheets/d/1dPjFt-bIQ5MrhIRULAur8cO-TJS1vbfS/edit?usp=sharing&ouid=114775878382175731948&rtpof=true&sd=true | done
T2.1 | Mapping of stakeholders | QSTURA | 2024-02-01 | A database of stakeholders extended to all partner countries (SP, IT,EL, HU, NL) with Fashion professionals, Fashion Companies,Students, Environmental Organization - with 10 members per category (50 members per partner, or 300 members in total). | Mapping of Stakeholders | done
T3.1 | Organisation of focus groups: Definition of target group, objectives and expected results | IDEC | 2024-03-15 | Both through the mapping of stakeholders from the previous WP and their existing networks, partners, guided by Blue Room, will organize structured focus groups to derive measurable results on what to include in the curriculum of the course | bri + qstura -- 2/2, IDEC -- 1/2, LHF -- 2/2, EKO - 2/2, MACHIAVELLI - 2/2 | ongoing
T3.2 | Creation of training curriculum | IDEC | 2024-03-18 | Based on the results of the focus groups from the previous task, Blue Room will create and deliver to partners a complete curriculum about the thematics of sustainable fashion procedures |  | ongoing
T3.3 | Developement of e-learning course contents | IDEC | 2024-03-18 | All partners under the leadership of IDEC will create contents based on expertise per module and deliver it complete with theoretical, practical content and self-assessment quiz. 24 |  | ongoing
T2.2 | Development of the specifications of the "Re-fashionable" digital platform | ALL PARTNERS | 2024-04-15 | IDEC will create and suggest in a report, based on its past experience the specifications (functions, modus-operandi, interface, menu etc.), of the platform. Partners will be able to comment and suggest improvements and/or changes. | T2.3 Platform definition – Re-fashionable | ongoing | https://forms.gle/h2HbjGBNyiBdmfcc9 | https://forms.gle/CUrKMCCYQ9i2a5NW8
T1.6 | 2nd meeting Szeged | EKO | 2024-04-24 | EKO will organize the 2nd project meeting and the “Pop up event”, both in Szeged. |  | ongoing
T3.4 | English | IDEC | 2024-05-31 | IDEC will supervise the final transformation of the created contents into a complete, well-crafted, all-inclusive course in respect to the curriculum and templates provided beforehand. |  | not started
T2.3 | Technical development of the platform | BRI | 2024-06-30 | BRI's technical staff will create and deliver the platform in a functional and user-friendly way. |  | not started
T3.5 | Peer review | EKO | 2024-07-15 | EKO will lead the Peer review, a task whose purpose is to check, evaluate, add any omitted content and perfect the course. This task will be done in an orderly, organized manner and suggestions will be implemented promptly. |  | not started
T2.4 | Translation of the digital platform | ALL PARTNERS | 2024-08-15 | Partners will deliver the texts to be included in the platform in their national languages. |  | not started
T3.6 | Translation | IDEC | 2024-08-31 | The translation to all partner languages by the respective partner in SP, IT, EL, HU, NL. The supervisor’s role will be to check that all contents have been translated and the national courses are ready for piloting. |  | not started
T3.7 | Pilot delivery of e-learning course | Machiavelli | 2024-09-01 | Machiavelli will guide the piloting by 15 members of the target groups per country. Each partner will deliver a piloting report. It will provide guidelines on the process, evaluation techniques and manner of implementation of improvements | In WP3, the school is responsible for Pilot delivery of e-learning course, overseeing that all partners contribute and submit their reports. Before and during the Summer Lab it will direct the Development of video - stories by participants and give them guidelines as needed. It will organize the Kick-off meeting in Lucca and the “Pop up event in Lucca”. | not started
T2.6 | Promoting the digital platform | BRI | 2024-09-07 | BRI will direct the partners on promoting the platform through publicity in relevant traditional and online media such as magazines, newspapers, portals, radio and blogs. |  | not started
T2.7 | Pilot operation of the platform - matchmaking | BRI | 2024-09-15 | BRI will direct the pilot usage of the platform by registered members, give instructions and support and implement technical changes if necessary. |  | not started
T1.8 | Interim report | BRI | 2024-09-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners, evaluating: -Collaboration and coordination -Risks and how they are mitigated -Understanding of roles, tasks and deliverables per partner -Partners’ expectations of the usage of project results |  | not started
T4.1 | Design of summer lab | LHF | 2024-09-30 | L.H.F. will prepare an agenda and design the tasks, find the ideal trainers and create an exact plan on how the project goals and the previous steps of the project will be integrated in the programme to better reach the project’s objectives. |  | not started
T4.2 | Call for participants | LHF | 2024-12-01 | L.H.F. will provide the other partner organizations ,with two different participant’s profiles, one for trainer/staff and one for student, so that each partner will have a clear and goal-oriented tool to select which people to send to the Lab. |  | not started
T1.7 | 3rd meeting Lucca | Machiavelli | 2024-12-15 | Machiavelli will organize the the 3rd project meeting and the “Pop up event in Lucca”. |  | not started
T4.3 | Selection of participants | LHF | 2025-01-01 | Partners will send a list of eligible profiles to L.H.F. and it will evaluate them and make the final selection according to predefined Key Performance Indicators. Thus, the final list of the 22 participants will be created. |  | not started
T4.4 | Preparation of participants | LHF | 2025-05-01 | L.H.F. will create a document with all the necessary information and things to be prepared and send it to all partners so that they can prepare their participants for the Lab |  | not started
T5.8 | Pop up event in Girona | BRI | 2025-06-01 | Blue Room will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia |  | not started
T5.9 | Pop up event in Piraeus | IDEC | 2025-06-01 | IDEC will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. |  | not started
T5.10 | Pop up event in Lucca | Machiavelli | 2025-06-01 | Machiavelli will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. |  | not started
T5.11 | Pop up event in Szeged | EKO | 2025-06-01 | EKO will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. |  | not started
T4.5 | Organisation of Summer lab | ALL PARTNERS | 2025-07-01 | L.H.F. will select the venue and brief the trainers involved and host the participants at its premises. All partners’ responsibility for that task is to make travel arrangements and send the participants. |  | not started
T5.5 | Publication of articles | EKO | 2025-07-01 | ΕΚΟ will oversee that in stage of the project, partners have composed and published interesting articles in their national media, regarding the new evolvements of the project. |  | not started
T5.6 | Social media creation and animation | EKO | 2025-07-01 | ΕΚΟ will create the Facebook and Instagram accounts, and make a schedule of posts for partners to follow so that there is constant and interesting presence and useful content generated. |  | not started
T5.7 | Transnational conference in Friesland | LHF | 2025-07-01 | It will be organised by LUF and will coincide with the culmination of the Summer Lab. The 30 participants of the event that are members of the target groups, will have the opportunity to learn the results of the Lab, presented by its own participants |  | not started
T4.6 | Summer Lab | LHF | 2025-08-01 | Development of video - stories from the Summer Lab: This final task is the responsibility of the Machiavelli Fashion School, which has the technical experience to guide participants in documenting the Summer Lab in 3 video stories. |  | not started
T1.9 | Final report | BRI | 2025-08-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners |  | not started
T1.2 | Project coordination and monitoring | BRI | 2025-08-31 | BRI will set up project management structure and processes and is also responsible for Project coordination and monitoring. It will write the Interim and Final project reports and make sure that all partners have contributed with their responsibilities as assigned by the proposal. |  | ongoing
T1.4 | Quality assurance activities and reports | BRI | 2025-08-31 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports, and ensure that improvements have been made when needed. |  | ongoing
T2.5 | On boarding activities for attracting platform subscribers | QSTURA | ask silvia! | Qstura will guide the partners on presenting the platform in Workshops, participation in events, fairs and conferences |  | not started
# | Activity | Responsible | Deadline | Output description | Link to output (if applicable) | Status
WP1: Project Management (BRI)
WP2: “Re-Fashionable” digital platform (BRI)
WP3: "Re-Fashionable" e-learning course (IDEC + Machiavelli)
WP4: Re-Fashionable Summer Lab (LHF)
WP5: Dissemination and impact (EKO)

## Quantitive + Qualitative indica
Indicators for Re-Fashionable
# | Activity | Responsible | Quantitative | Qualitative | Status
WP2: “Re-Fashionable” digital platform (BRI)
T2.1 | Mapping of stakeholders | QSTURA | 20 registrations to platform per partner (120 registered members in total), 5 articles per partner (30 articles in total) to the platform’s Blog 10 resources per partner (60 resources in total) such as articles, videos, or links uploaded at the section “I seek” of the platform. Workshops, participation in events, fairs and conferences Target: 10 organisations per country 3 posts on each partner’s social media, 3 articles in magazines, or newspapers or relevant fashion portals, 3 presentations in conferences or meetings at a European level = Total 9 activities per partner or 54 activities in total for the publicity of the platform. A database of target group members (Fashion professionals, Fashion Companies, Students, Environmental Organisation) with 10 members per category (50 members per partner, or 300 members in total). Platform in all partner languages, plus English. (ES, IT, EL, HU, NL) At least 120 members of the fashion world in partner countries (such as fashion professionals, companies, fashion schools, environmental organisations) will register to the “Re-Fashionable platform”. At least 300 members of the target groups will be reached out to and communicate with for the creation of the project database (50 members per partner, or 300 members in total). Through the publicity and the onboarding campaigns implemented by the partnership, thousands of European members of the fashion industry as well as consumers, trainers and members of European organizations will be reached and become more aware of the environmental hazards of irresponsible fashion processes and purchasing decisions and will implement changes in their behavior | At least 80% satisfaction as derived from the evaluation questionnaire of the platform regarding: The user-friendliness of the platform The resources available at the platform The professional usefulness of the platform regarding sustainability networking in the fashion industry. The likelihood that registered members will suggest the use of the platform to other members of the fashion industry. | ongoing
T2.2 | Development of the specifications of the "Re-fashionable" digital platform | ALL PARTNERS |  |  | not started
T2.3 | Technical development of the platform | BRI |  |  | not started
T2.4 | Translation of the digital platform | ALL PARTNERS |  |  | not started
T2.5 | On boarding activities for attracting platform subscribers | QSTURA |  |  | not started
T2.6 | Promoting the digital platform | BRI |  |  | not started
T2.7 | Pilot operation of the platform - matchmaking | BRI |  |  | not started
WP3: "Re-Fashionable" e-learning course (IDEC)
T3.1 | Organisation of focus groups: Definition of target group, objectives and expected results | IDEC | A well researched complete training curriculum regarding sustainable fashion. An e-learning course regarding circular fashion and sustainability of the sector from a 360 point of view. Duration of course: 24 hours of training. Languages: EN, EL, ES, IT, HU, NL. e-learning course in an open access, Moodle environment. A pilot delivery of 15 persons per partner country (total of 90 persons), all members of target groups i.e. (industry professionals, students, fashion schools and environmental organizations interested in the topic of sustainable fashion). A report per partner (6 reports) regarding the course’s possible omissions, improvements, and corrections that are to be done. | Min 80% satisfaction from the participants of the pilot training regarding: The activity’s organization; The knowledge and helpfulness of its trainers; How well participants were briefed on the e-learning course; How helpful is course regarding sustainability in the fashion industry ; How applicable is the course to their profession and/or studies; | ongoing
T3.2 | Creation of training curriculum | IDEC |  |  | not started
T3.3 | Developement of e-learning course contents | IDEC |  |  | not started
T3.4 | English | IDEC |  |  | not started
T3.5 | Peer review | EKO |  |  | not started
T3.6 | Translation | IDEC |  |  | not started
T3.7 | Pilot delivery of e-learning course | Machiavelli |  |  | not started
WP4: Re-Fashionable Summer Lab (LHF)
T4.1 | Design of summer lab | LHF | In the Summer Lab there will be 3 trainers or staff members from each partner organisation + 5 students from each participating fashion school to attend for 4 days in Friesland, The Netherlands. Total participants: 22 people 1 preparation document sent out to participants 2 months before the activity which will include basic knowledge about sustainability issues, expectations and main areas of brainstorming ideas that they must prepare. 1 Business Canvas Model based business plan regarding a novel and innovative sustainability project or business related to a company, organisation or fashion school. 1 set of 3 video stories narrating the Preparation of the Lab, the Work-in-Progress and finally, the Lessons Learned and the presentation of the Business Plan | At least 80% satisfaction of participants from the Summer Lab regarding: The activity’s organization. The venue chosen. The knowledge and helpfulness of the facilitators. How well participants were prepared in advance. How inspirational was the Summer Lab in applying sustainability principles to their organisation, business or school. How confident they feel to transfer the competences and knowledge gained, to others. | not started
T4.2 | Call for participants | LHF |  |  | not started
T4.3 | Selection of participants | LHF |  |  | not started
T4.4 | Preparation of participants | LHF |  |  | not started
T4.5 | Organisation of Summer lab | ALL PARTNERS |  |  | not started
T4.6 | Summer Lab | LHF |  |  | not started
WP5: Dissemination and impact (EKO)
T5.1 | Develop Dissemination and Exploitation plan | EKO | 5 Multiplier events: Transnational conference in Friesland, NL, Pop up event in Girona, ES, Pop up event in Piraeus, GR, Pop up event in Lucca, IT, Pop up event in Budapest, HU. 30 participants per event (150 in total) with profiles being: Fashion professional, or representative of a fashion company, or Fashion Students, or Trainer at Fashion School, or Member of Environmental Organisation, or member of local or national authority focusing on sustainability issues. 300 followers to the project’s Facebook page 200 followers to the project’s Instagram account 2,000 visits to the project’s website over the period of 2 years Maintenance of the project website for 5 years 4 newsletters with at least 600 recipients (100 per partner). 1 informative leaflet in all partner languages (ES, IT, EL, NL,HU,EN) 2 webinars to attract participants 6 articles in relevant Media (magazine, newspaper, portal) - one per partner in its own country. | A min of 80% satisfaction at each activity or event. Measured in dimensions such as: Οrganizational aspect of the events How interesting participants found the event or the piloting How user-friendly subscribed members found the platform How inclusive, complete and impactful they found the course. How attractive, well designed and helpful they found the platform and the course How likely are participants to disseminate the project results to colleagues and classmates. How knowledgeable and helpful about the discussed topics were trainers and partners’ staf involved at every activity or task. | done
T5.2 | Development of the project identity (logos, graphic templates) | EKO |  |  | ongoing
T5.3 | Development of project website | EKO |  |  | ongoing
T5.4 | Development of leaflet and roll-up | EKO |  |  | ongoing
T5.5 | Publication of articles | EKO |  |  | ongoing
T5.6 | Social media creation and animation | EKO |  |  | done
T5.7 | Transnational conference in Friesland | LHF |  |  | not started
T5.8 | Pop up event in Girona | BRI |  |  | not started
T5.9 | Pop up event in Piraeus | IDEC |  |  | not started
T5.10 | Pop up event in Lucca | Machiavelli |  |  | not started
T5.11 | Pop up event in Szeged | EKO |  |  | not started

## Partners (Contacts + Info)
Entity |  | WP Leader | Country | Email | Website
(BRI) Blue Room Innovation | ES | WP1, WP2 | ES | denisa@blueroominnovation.com
(QSTURA) Grup Qstura 2017 SL | ES | WP1, WP2 | ES | Sílvia Castelló Duran <silvia@qstura.cat>
(IDEC) Aintek Sumvouloi Epicheiriseon | EL | WP3 | EL | Eleni Fazaki e.fazaki@idec.gr
(Machiavelli) Instituto di Instruzione Superiore N. Machiavelli | IT | WP3 | IT | malagnino.antonella@istitutomachiavelli.edu.it | http://www.liceo-machiavelli.it/
(EKO) Association for creativ education | HU | WP5 | HU | vizinoemi2@gmail.com
(LHF) Learning Hub Friesland | NL | WP4 | NL | frank@learninghubfriesland.nl