## TODO LIST --> general view
# | Activity | Responsible | Deadline | Output description | Link to output (if applicable) | Status
WP1: Project Management (BRI)
T1.1 | Set up project management structure and processes | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports and ensure that improvements have been made when needed. | T1.1 REFA PM Handbook.pdf | done
T1.2 | Project coordination and monitoring | BRI | 2025-08-31 | BRI will set up project management structure and processes and is also responsible for Project coordination and monitoring. It will write the Interim and Final project reports and make sure that all partners have contributed with their responsibilities as assigned by the proposal. | TODO for Re-Fashionable | done
T1.3 | Set up quality assurance plan | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports, and ensure that improvements have been made when needed. | T1.3 REFA Quality Assurance Plan.pdf | done
T1.4 | Quality assurance activities and reports | BRI | 2024-02-29 | M6 Quality Report | T1.4.1 REFA Quality Report M6.pdf | done
|  | EKO | 2024-08-31 | M12 Quality Report | T1.4.2 REFA Quality Report M12 | done
|  | EKO | 2025-02-28 | M18 Quality Report | T1.4.3 REFA Quality Report M18.pdf | done
|  | EKO | 2025-08-31 | M24 Quality Report | T1.4.4 REFA Quality Report M24.pdf | done
T1.5 | Kick off meeting in Girona | BRI | 2023-12-12 | A kick-off meeting will be hosted in Lucca by the Machiavelli --> in Girona by BRI, changed | T1.5 KOM ATTENDANCE LIST, signed.pdf | done
T1.6 | 2nd meeting Budapest | EKO | 2024-04-24 | EKO will organize the 2nd project meeting and the “Pop up event”, both in Szeged. | T1.6.1 Attendance_sheet_Szeged_Discussion_24_April_2024.pdf | done
T1.7 | 3rd meeting Lucca | Machiavelli | 2024-12-15 | Machiavelli will organize the the 3rd project meeting and the “Pop up event in Lucca”. | T1.7 attendance_3rdmeeting.pdf | done
T1.8 | Interim report | EKO | 2024-09-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners, evaluating: -Collaboration and coordination -Risks and how they are mitigated -Understanding of roles, tasks and deliverables per partner -Partners’ expectations of the usage of project results | T1.8 - The Interim Project Management Report.pdf | done
|  | BRI |  | PM Interim Report |  | done
T1.9 | Final report | BRI | 2025-08-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners | T1.9 Final PM Report.pdf | done
T2.1 | Mapping of stakeholders | QSTURA | 2024-02-01 | A database of stakeholders extended to all partner countries (SP, IT,EL, HU, NL) with Fashion professionals, Fashion Companies,Students, Environmental Organization - with 10 members per category (50 members per partner, or 300 members in total). | Mapping of Stakeholders | done
[5 empty] | T2.1 - Report - Mapping of Stakeholders.pdf | done
T2.2 | Development of the specifications of the "Re-fashionable" digital platform | BRI | 2024-04-15 | IDEC will create and suggest in a report, based on its past experience the specifications (functions, modus-operandi, interface, menu etc.), of the platform. Partners will be able to comment and suggest improvements and/or changes. | T2.2 - Development of the specifications of the Re-fashionable digital platform.pdf | done
T2.3 | Technical development of the platform | BRI | 2024-09-30 | BRI's technical staff will create and deliver the platform in a functional and user-friendly way. | Dashboard - Re-fashionable | done
T2.4 | Translation of the digital platform | ALL PARTNERS | 2024-09-30 | Partners will deliver the texts to be included in the platform in their national languages. | (T2.4) Table for Platform Translations - REFA | done |  | “Re-fashionable TO-DO List”
T2.5 | On boarding activities for attracting platform subscribers | QSTURA | 2024-11-30 | Qstura will guide the partners on presenting the platform in Workshops, participation in events, fairs and conferences | T2.5 LETTERS OF SUPPORT and Onboarding Activities (1).pdf | done
T2.6 | Promoting the digital platform | QSTURA | 2024-12-16 | Qstura will direct the partners on promoting the platform through publicity in relevant traditional and online media such as magazines, newspapers, portals, radio and blogs. 3 posts on each partner’s social media, 3 articles in magazines, or newspapers or relevant fashion portals, 3 presentations in conferences or meetings at a European level = Total 9 activities per partner or 54 activities in total for the publicity of the platform. | T2.6 - Promoting the Re-fashionable PLATFORM.pdf | done
T2.7 | Pilot operation of the platform - matchmaking | BRI | 2024-12-16 | BRI will direct the pilot usage of the platform by registered members, give instructions and support and implement technical changes if necessary. Llista per country de les 15 persones del pilot (BRI to prepare template, EKO to prepare Quality Evaluation). Email to stakeholders about platform/pilot; missatge al admin sobre pilot abans del 15/03 | T2.7 Pilot operation of the platform Full Report.pdf | done
WP3: "Re-Fashionable" e-learning course (IDEC + Machiavelli)
T3.1 | Organisation of focus groups: Definition of target group, objectives and expected results | IDEC | 2024-02-28 | Both through the mapping of stakeholders from the previous WP and their existing networks, partners, guided by Blue Room, will organize structured focus groups to derive measurable results on what to include in the curriculum of the course | WP3T3.1 REFA Focus Group Synthesis Report (3).pdf | done
T3.2 | Creation of training curriculum | IDEC | 2024-04-30 | Based on the results of the focus groups from the previous task, Blue Room will create and deliver to partners a complete curriculum about the thematics of sustainable fashion procedures | WP3_T3.2 Re-Fashionable e-learning Curriculum.pdf | done
T3.3 | Developement of e-learning course contents | IDEC | 2024-06-30 | All partners under the leadership of IDEC will create contents based on expertise per module and deliver it complete with theoretical, practical content and self-assessment quiz. 24 | T3.3 e-LEARNING COURSE LESSON CONTENTS | done
T3.4 | English | IDEC | 2024-06-30 | IDEC will supervise the final transformation of the created contents into a complete, well-crafted, all-inclusive course in respect to the curriculum and templates provided beforehand. | T3.4 THE GREEN THREAD COURSE-ready for PEER REVIEW | done | “Re-fashionable TO-DO List”
T3.5 | Peer review | EKO | 2024-07-15 | EKO will lead the Peer review, a task whose purpose is to check, evaluate, add any omitted content and perfect the course. This task will be done in an orderly, organized manner and suggestions will be implemented promptly. | T3.5 peer review report.pdf | done
T3.6 | Translation | IDEC | 2024-08-31 | The translation to all partner languages by the respective partner in SP, IT, EL, HU, NL. The supervisor’s role will be to check that all contents have been translated and the national courses are ready for piloting. | https://platform.refashionable.eu/course | done
T3.7 | Pilot delivery of e-learning course | Machiavelli | 2024-12-16 | Machiavelli will guide the piloting by 15 members of the target groups per country. Each partner will deliver a piloting report. It will provide guidelines on the process, evaluation techniques and manner of implementation of improvements | T3.7 Pilot delivery of e-learning course.pdf | done
WP4: Re-Fashionable Summer Lab (LHF)
T4.1 | Design of summer lab | LHF | 2024-09-30 | L.H.F. will prepare an agenda and design the tasks, find the ideal trainers and create an exact plan on how the project goals and the previous steps of the project will be integrated in the programme to better reach the project’s objectives. | T4.1 Design of the Summer Lab WP4 (LHF) (1).pdf | done
T4.2 | Call for participants | LHF | 2024-12-01 | L.H.F. will provide the other partner organizations ,with two different participant’s profiles, one for trainer/staff and one for student, so that each partner will have a clear and goal-oriented tool to select which people to send to the Lab. | T4.2 CALL FOR PARTICIPANTS - Profiles of ideal participants for the SummerLab - WP4 (LHF) (1).pdf | done
T4.3 | Selection of participants | LHF | 2025-01-01 | Partners will send a list of eligible profiles to L.H.F. and it will evaluate them and make the final selection according to predefined Key Performance Indicators. Thus, the final list of the 22 participants will be created. | T4.3 Selection of participants for the Summer Lab | done
T4.4 | Preparation of participants | LHF | 2025-05-01 | L.H.F. will create a document with all the necessary information and things to be prepared and send it to all partners so that they can prepare their participants for the Lab | T4.4 Re-fa Summer Lab - agenda, travel & accommodation info (4).pdf | done
T4.5 | Organisation of Summer lab | ALL PARTNERS | 2025-07-01 | L.H.F. will select the venue and brief the trainers involved and host the participants at its premises. All partners’ responsibility for that task is to make travel arrangements and send the participants. | Re-fa Summer Lab - full agenda.pdf | done
T4.6 | Summer Lab | LHF | 2025-08-01 | Development of video - stories from the Summer Lab: This final task is the responsibility of the Machiavelli Fashion School, which has the technical experience to guide participants in documenting the Summer Lab in 3 video stories. | T4.6 RE-FA Summer Lab report.pdf | done
WP5: Dissemination and impact (EKO)
T5.1 | Develop Dissemination and Exploitation plan | EKO | 2023-12-31 | A 360o (from concept to materialization to feedback and application of corrective actions) plan will be created by EKO and delivered at the kickoff meeting. | T5.1 ReFa_Dissemination and exploitation plan_jan_15.docx.pdf | done
T5.2 | Development of the project identity (logos, graphic templates): an attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | EKO | 2023-12-31 | An attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | T.5.2.pdf | done
T5.3 | Development of project website | EKO | 2024-01-31 | ΕΚΟ will create an inclusive and user friendly website in EN, EL, SP,IT, HU, NL update it as the project progresses and track visitors. | Re-fashionable – Empowering The Fashion Industry Through Sustainable Collaboration (refashionable.eu) | done | TABLE FOR WEBSITE TRANSLATIONS - REFA
T5.4 | Development of leaflet and roll-up | EKO | 2024-01-31 | EKO will also create a leaflet and a rollup and deliver it to partners to translate and adapt so that they can use them for communicating with targets and during events. | T.5.4.pdf | done
T5.5 | Publication of articles | EKO | 2025-07-01 | ΕΚΟ will oversee that in stage of the project, partners have composed and published interesting articles in their national media, regarding the new evolvements of the project. | T5.5 - Publications and articles.pdf | done
T5.6 | Social media creation and animation | EKO | 2025-07-01 | ΕΚΟ will create the Facebook and Instagram accounts, and make a schedule of posts for partners to follow so that there is constant and interesting presence and useful content generated. | T5.6 ReFa_Dissemination and exploitation report.pdf | done
T5.7 | Transnational conference in Friesland | LHF | 2025-07-01 | It will be organised by LUF and will coincide with the culmination of the Summer Lab. The 30 participants of the event that are members of the target groups, will have the opportunity to learn the results of the Lab, presented by its own participants | T5.7 Transnational conference in Friesland.pdf | done
T5.8 | Pop up event in Girona | QSTURA | 2025-06-01 | Blue Room will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | T5.8 Pop Up Event in Girona.pdf | done
T5.9 | Pop up event in Piraeus | IDEC | 2025-06-01 | IDEC will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | T5.9 REFA Pop-up event report - Greece.pdf | done
T5.10 | Pop up event in Lucca | Machiavelli | 2025-06-01 | Machiavelli will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | T5.10 Pop Up Event in Lucca.pdf | done
T5.11 | Pop up event in Szeged | EKO | 2025-06-01 | EKO will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | T5.11 - Pop-Up Event in Szeged.pdf | done

## TODO LIST --> view with filters
# | Activity | Responsible | Deadline | Output description | Link to output (if applicable) | Status
T1.5 | Kick off meeting in Girona | BRI | 2023-12-12 | A kick-off meeting will be hosted in Lucca by the Machiavelli --> in Girona by BRI, changed | T1.5 KOM ATTENDANCE LIST, signed.pdf | done
T5.1 | Develop Dissemination and Exploitation plan | EKO | 2023-12-31 | A 360o (from concept to materialization to feedback and application of corrective actions) plan will be created by EKO and delivered at the kickoff meeting. | T5.1 ReFa_Dissemination and exploitation plan_jan_15.docx.pdf | done
T5.2 | Development of the project identity (logos, graphic templates): an attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | EKO | 2023-12-31 | An attractive, relevant and eye-catching graphic identity will be delivered by EKO so that partners can use it in all communication tasks and deliverables. | T.5.2.pdf | done
T1.1 | Set up project management structure and processes | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports and ensure that improvements have been made when needed. | TODO for Re-Fashionable | done
T1.1 | Set up project management structure and processes | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports and ensure that improvements have been made when needed. | T1.1 REFA PM Handbook.pdf | done
T1.3 | Set up quality assurance plan | BRI | 2024-01-30 | BRI will be responsible for the Quality Assurance of the project, create the QA Plan, guide activities, write and deliver reports, and ensure that improvements have been made when needed. | T1.3 REFA Quality Assurance Plan.pdf | done
T5.3 | Development of project website | BRI | 2024-01-31 | ΕΚΟ will create an inclusive and user friendly website in EN, EL, SP,IT, HU, NL update it as the project progresses and track visitors. | Re-fashionable – Empowering The Fashion Industry Through Sustainable Collaboration (refashionable.eu) | done
T5.4 | Development of leaflet and roll-up | EKO | 2024-01-31 | EKO will also create a leaflet and a rollup and deliver it to partners to translate and adapt so that they can use them for communicating with targets and during events. | T.5.4.pdf | done
T2.1 | Mapping of stakeholders | QSTURA | 2024-02-01 | A database of stakeholders extended to all partner countries (SP, IT,EL, HU, NL) with Fashion professionals, Fashion Companies,Students, Environmental Organization - with 10 members per category (50 members per partner, or 300 members in total). | Mapping of Stakeholders | done
T2.1 | Mapping of stakeholders | QSTURA | 2024-02-01 |  | T2.1 - Report - Mapping of Stakeholders.pdf | done
T1.4 | Quality assurance activities and reports | BRI | 2024-02-29 | M6 Quality Report | T1.4.1 REFA Quality Report M6.pdf | done
T3.1 | Organisation of focus groups: Definition of target group, objectives and expected results | IDEC | 2024-03-15 | Both through the mapping of stakeholders from the previous WP and their existing networks, partners, guided by Blue Room, will organize structured focus groups to derive measurable results on what to include in the curriculum of the course | WP3T3.1 REFA Focus Group Synthesis Report.pdf | done
T3.2 | Creation of training curriculum | IDEC | 2024-03-18 | Based on the results of the focus groups from the previous task, Blue Room will create and deliver to partners a complete curriculum about the thematics of sustainable fashion procedures | WP3_T3.2 Re-Fashionable e-learning Curriculum.pdf | done
T2.2 | Development of the specifications of the "Re-fashionable" digital platform | ALL PARTNERS | 2024-04-15 | IDEC will create and suggest in a report, based on its past experience the specifications (functions, modus-operandi, interface, menu etc.), of the platform. Partners will be able to comment and suggest improvements and/or changes. | T2.2 - Development of the specifications of the Re-fashionable digital platform.pdf | done | https://forms.gle/h2HbjGBNyiBdmfcc9
T1.6 | 2nd meeting Szeged | EKO | 2024-04-24 | EKO will organize the 2nd project meeting and the “Pop up event”, both in Szeged. | T1.6.2 Attendance_sheet_Szeged_Study_trip_25_April_2024.pdf | done | https://ap.adminproject.eu/files/index/getFile/3269/698564
T3.3 | Developement of e-learning course contents | IDEC | 2024-06-23 | All partners under the leadership of IDEC will create contents based on expertise per module and deliver it complete with theoretical, practical content and self-assessment quiz. 24 | T3.3 e-LEARNING COURSE LESSON CONTENTS | done
T3.4 | English | IDEC | 2024-06-30 | IDEC will supervise the final transformation of the created contents into a complete, well-crafted, all-inclusive course in respect to the curriculum and templates provided beforehand. | T3.4 THE GREEN THREAD COURSE-ready for PEER REVIEW | done
T3.5 | Peer review e-course | EKO | 2024-08-12 | EKO will lead the Peer review, a task whose purpose is to check, evaluate, add any omitted content and perfect the course. This task will be done in an orderly, organized manner and suggestions will be implemented promptly. | T3.5 peer review report.pdf | done
T3.6 | Translation of e-learning course | IDEC | 2024-09-15 | The translation to all partner languages by the respective partner in SP, IT, EL, HU, NL. The supervisor’s role will be to check that all contents have been translated and the national courses are ready for piloting. | directly on the platform | done
T1.4 | Quality assurance activities and reports | EKO | 2024-09-30 | M12 Quality Report (Interim QA Report) | T1.4.2 REFA Quality Report M12 | done
T2.3 | Technical development of the platform | BRI | 2024-09-30 | BRI's technical staff will create and deliver the platform in a functional and user-friendly way. | Dashboard - Re-fashionable | done
T1.8 | Interim report | BRI | 2024-09-30 | PM Interim Report | T1.8 - The Interim Project Management Report.pdf | done
T4.1 | Design of summer lab | LHF | 2024-09-30 | L.H.F. will prepare an agenda and design the tasks, find the ideal trainers and create an exact plan on how the project goals and the previous steps of the project will be integrated in the programme to better reach the project’s objectives. | T4.1 Design of the Summer Lab WP4 (LHF) (1).pdf | done
T2.4 | Translation of the digital platform | ALL PARTNERS | 2024-10-14 | Partners will deliver the texts to be included in the platform in their national languages. | Dashboard - Re-fashionable | done
T2.4.1 | E-learning course upload on the REFA Platform | ALL PARTNERS | 2024-11-30 | All partners are to upload the tranlated e-learning course contents on the REFA Platform. Instructions --> | https://platform.refashionable.eu/course | done
T4.2 | Call for participants | LHF | 2024-12-01 | L.H.F. will provide the other partner organizations ,with two different participant’s profiles, one for trainer/staff and one for student, so that each partner will have a clear and goal-oriented tool to select which people to send to the Lab. | T4.2 CALL FOR PARTICIPANTS - Profiles of ideal participants for the SummerLab - WP4 (LHF) (1).pdf | done
T1.7 | 3rd meeting Lucca | Machiavelli | 2024-12-05 | Machiavelli will organize the the 3rd project meeting and the “Pop up event in Lucca”. | T1.7 - minutes 05.12.2024 - 3RD CONSORTIUM MEETING in Italy (1).pdf | done
T4.3 | Selection of participants | ALL PARTNERS | 2025-02-28 | Partners will send a list of eligible profiles to L.H.F. and it will evaluate them and make the final selection according to predefined Key Performance Indicators. Thus, the final list of the 22 participants will be created. | T4.3 Selection of participants for the Summer Lab | done
T1.4 | Quality assurance activities and reports | EKO | 2025-02-28 | M18 Quality Report | T1.4.3 REFA Quality Report M18.pdf | done
T2.7 | Pilot operation of the platform - matchmaking | BRI | 2025-03-28 | BRI will direct the pilot usage of the platform by registered members, give instructions and support and implement technical changes if necessary. | T2.7 Pilot operation of the platform Full Report.pdf | done
T3.7 | Pilot delivery of e-learning course | Machiavelli | 2025-04-07 | Machiavelli will guide the piloting by 15 members of the target groups per country. Each partner will deliver a piloting report. It will provide guidelines on the process, evaluation techniques and manner of implementation of improvements. Missing: IDEC, MACHIAVELLI, EKO, LHF | T3.7 - Guidelines for Piloting the Re-Fashionable E-Learning Course.pdf | late
T2.5 | On boarding activities for attracting platform subscribers | QSTURA | 2025-04-07 | Qstura will guide the partners on presenting the platform in Workshops, participation in events, fairs and conferences. Target: 10 organisations per country - sign 10 affiliation letters. Missing: ALL PARTNERS | Affiliation template | late
T2.6 | Promoting the digital platform | QSTURA | 2025-04-07 | QSTURA will direct the partners on promoting the platform through publicity in relevant traditional and online media such as magazines, newspapers, portals, radio and blogs.3 posts on each partner’s social media, 3 articles in magazines, or newspapers or relevant fashion portals, 3 presentations in conferences or meetings at a European level = Total 9 activities per partner or 54 activities in total for the publicity of the platform. |  | late
T4.4 | Preparation of participants | LHF | 2025-05-01 | L.H.F. will create a document with all the necessary information and things to be prepared and send it to all partners so that they can prepare their participants for the Lab | T4.4 Re-fa Summer Lab - agenda, travel & accommodation info (4).pdf | done
T4.5 | Organisation of Summer lab | ALL PARTNERS | 2025-06-20 | L.H.F. will select the venue and brief the trainers involved and host the participants at its premises. All partners’ responsibility for that task is to make travel arrangements and send the participants. |  | done
T5.7 | Transnational conference in Friesland | LHF | 2025-06-20 | It will be organised by LUF and will coincide with the culmination of the Summer Lab. The 30 participants of the event that are members of the target groups, will have the opportunity to learn the results of the Lab, presented by its own participants | report? | ongoing
T4.6 | Summer Lab | LHF | 2025-06-20 | Development of video - stories from the Summer Lab: This final task is the responsibility of the Machiavelli Fashion School, which has the technical experience to guide participants in documenting the Summer Lab in 3 video stories. | videos / stories? | ongoing
T5.5 | Publication of articles | EKO | 2025-07-01 | ΕΚΟ will oversee that in stage of the project, partners have composed and published interesting articles in their national media, regarding the new evolvements of the project. | 3 articles from wp2 | ongoing
T5.6 | Social media creation and animation | EKO | 2025-07-01 | ΕΚΟ will create the Facebook and Instagram accounts, and make a schedule of posts for partners to follow so that there is constant and interesting presence and useful content generated. | ongoing | ongoing
T5.8 | Pop up event in Girona | QSTURA | 2025-08-18 | Blue Room will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia | 30 participants / event | not started
T5.9 | Pop up event in Piraeus | IDEC | 2025-08-18 | IDEC will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | 30 participants / event | not started
T5.10 | Pop up event in Lucca | Machiavelli | 2025-08-18 | Machiavelli will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | 30 participants / event | not started
T5.11 | Pop up event in Szeged | EKO | 2025-08-18 | EKO will organize the event to spread project results to target groups. It will create the agenda, select the venue, invite target group members, recruit qualified speakers from the fashion industry, environmental organizations and academia. | 30 participants / event | not started
T1.9 | Final report | BRI | 2025-08-30 | An internal quality assurance report will be delivered at interim and final report, based on respective questionnaires answered by all partners | ongoing | ongoing
T1.4 | Quality assurance activities and reports | EKO | 2025-08-31 | M24 Quality Report | ongoing | not started
T1.2 | Project coordination and monitoring | BRI | 2025-08-31 | BRI will set up project management structure and processes and is also responsible for Project coordination and monitoring. It will write the Interim and Final project reports and make sure that all partners have contributed with their responsibilities as assigned by the proposal. |  | ongoing
2025
WP1: Project Management (BRI)
WP2: “Re-Fashionable” digital platform (BRI)
WP3: "Re-Fashionable" e-learning course (IDEC + Machiavelli)
WP4: Re-Fashionable Summer Lab (LHF)
WP5: Dissemination and impact (EKO)

## Quantitive + Qualitative indica
Indicators for Re-Fashionable
# | Quanti |  | Link output (if any) | Info/status | Quali
WP2: “Re-Fashionable” digital platform (BRI + Qstura)
1 (8) | 20 registrations to platform per partner (120 registered members in total), | done |  |  | At least 80% satisfaction as derived from the evaluation questionnaire of the platform regarding: The user-friendliness of the platform The resources available at the platform The professional usefulness of the platform regarding sustainability networking in the fashion industry. The likelihood that registered members will suggest the use of the platform to other members of the fashion industry.
2 | 5 articles per partner (30 articles in total) to the platform’s Blog | done |  | 12/30
3 | 10 resources per partner (60 resources in total) such as articles, videos, or links uploaded at the section “I seek” of the platform. | done |  | same resources as in the e-learning course
4 | Workshops, participation in events, fairs and conferences Target: 10 organisations per country | done |  | T2.5 - Workshops, participation in events, fairs and conferences Target: 10 organisations per country
5 | 3 posts on each partner’s social media, 3 articles in magazines, or newspapers or relevant fashion portals, 3 presentations in conferences or meetings at a European level = Total 9 activities per partner or 54 activities in total for the publicity of the platform. | done |  | T2.6
6 (9) | A database of target group members (Fashion professionals, Fashion Companies, Students, Environmental Organisation) with 10 members per category (50 members per partner, or 300 members in total). | done | T2.1 Mapping of Stakeholders | WP2 CONTROL - REFA
7 | Platform in all partner languages, plus English. (ES, IT, EL, HU, NL) | not started
8 (1) | At least 120 members of the fashion world in partner countries (such as fashion professionals, companies, fashion schools, environmental organisations) will register to the “Re-Fashionable platform”. | not started
9 (6) | At least 300 members of the target groups will be reached out to and communicate with for the creation of the project database (50 members per partner, or 300 members in total). | ongoing | T2.1 Mapping of Stakeholders
10 | Through the publicity and the onboarding campaigns implemented by the partnership, thousands of European members of the fashion industry as well as consumers, trainers and members of European organizations will be reached and become more aware of the environmental hazards of irresponsible fashion processes and purchasing decisions and will implement changes in their behavior | ongoing
WP3: "Re-Fashionable" e-learning course (IDEC + Machiavelli)
11 | A well researched complete training curriculum regarding sustainable fashion. | done | WP3_T3.2 Re-Fashionable e-learning Curriculum.pdf |  | Min 80% satisfaction from the participants of the pilot training regarding: The activity’s organization; The knowledge and helpfulness of its trainers; How well participants were briefed on the e-learning course; How helpful is course regarding sustainability in the fashion industry ; How applicable is the course to their profession and/or studies;
12 | An e-learning course regarding circular fashion and sustainability of the sector from a 360 point of view. | done
13 | Duration of course: 24 hours of training. | done
14 | Languages: EN, EL, ES, IT, HU, NL. | ongoing
15 | e-learning course in an open access, Moodle environment. | ongoing
16 | A pilot delivery of 15 persons per partner country (total of 90 persons), all members of target groups i.e. (industry professionals, students, fashion schools and environmental organizations interested in the topic of sustainable fashion). | not started |  | octiber 2024
17 | A report per partner (6 reports) regarding the course’s possible omissions, improvements, and corrections that are to be done. | not started |  | december 2024
WP4: Re-Fashionable Summer Lab (LHF)
18 | In the Summer Lab there will be 3 trainers or staff members from each partner organisation + 5 students from each participating fashion school to attend for 4 days in Friesland, The Netherlands. Total participants: 22 people | not started |  |  | At least 80% satisfaction of participants from the Summer Lab regarding: The activity’s organization. The venue chosen. The knowledge and helpfulness of the facilitators. How well participants were prepared in advance. How inspirational was the Summer Lab in applying sustainability principles to their organisation, business or school. How confident they feel to transfer the competences and knowledge gained, to others.
19 | 1 preparation document sent out to participants 2 months before the activity which will include basic knowledge about sustainability issues, expectations and main areas of brainstorming ideas that they must prepare. | not started
20 | 1 Business Canvas Model based business plan regarding a novel and innovative sustainability project or business related to a company, organisation or fashion school. | not started
21 | 1 set of 3 video stories narrating the Preparation of the Lab, the Work-in-Progress and finally, the Lessons Learned and the presentation of the Business Plan | not started
WP5: Dissemination and impact (EKO)
24 | 5 Multiplier events: Transnational conference in Friesland, NL, Pop up event in Girona, ES, Pop up event in Piraeus, GR, Pop up event in Lucca, IT, Pop up event in Budapest, HU. | not started |  |  | A min of 80% satisfaction at each activity or event. Measured in dimensions such as: Οrganizational aspect of the events How interesting participants found the event or the piloting How user-friendly subscribed members found the platform How inclusive, complete and impactful they found the course. How attractive, well designed and helpful they found the platform and the course How likely are participants to disseminate the project results to colleagues and classmates. How knowledgeable and helpful about the discussed topics were trainers and partners’ staf involved at every activity or task.
25 | 30 participants per event (150 in total) with profiles being: Fashion professional, or representative of a fashion company, or Fashion Students, or Trainer at Fashion School, or Member of Environmental Organisation, or member of local or national authority focusing on sustainability issues. | not started
26 | 300 followers to the project’s Facebook page | not started
27 | 200 followers to the project’s Instagram account | not started
28 | 2,000 visits to the project’s website over the period of 2 years | ongoing | Google analytics?
29 | Maintenance of the project website for 5 years | done | Re-fashionable – Empowering The Fashion Industry Through Sustainable Collaboration (refashionable.eu)
30 | 4 newsletters with at least 600 recipients (100 per partner). | ongoing
31 | 1 informative leaflet in all partner languages (ES, IT, EL, NL,HU,EN) | done | T.5.4.pdf
32 | 2 webinars to attract participants | not started |  | per partner? in tota?
33 | 6 articles in relevant Media (magazine, newspaper, portal) - one per partner in its own country. | not started

## Partners (Contacts + Info)
| Entity |  | WP Leader | Country | Email | Website
P1 | (BRI) Blue Room Innovation | ES | WP1, WP2 | ES | denisa@blueroominnovation.com
P2 | (QSTURA) Grup Qstura 2017 SL | ES | WP1, WP2 | ES | Sílvia Castelló Duran <silvia@qstura.cat>
P3 | (IDEC) Aintek Sumvouloi Epicheiriseon | EL | WP3 | EL | Eleni Fazaki e.fazaki@idec.gr
P4 | (Machiavelli) Instituto di Instruzione Superiore N. Machiavelli | IT | WP3 | IT | malagnino.antonella@istitutomachiavelli.edu.it | http://www.liceo-machiavelli.it/
P5 | (EKO) Association for creativ education | HU | WP5 | HU | vizinoemi2@gmail.com
P6 | (LHF) Learning Hub Friesland | NL | WP4 | NL | frank@learninghubfriesland.nl